## Sheet1
| Key |  | Activity on track
Activity delayed
Activity rescheduled
|  | 2022-03-04 | Deadline or date of activity
| Q1 |  |  | Q2 |  |  |  | Owner of activity | Notes
Activity | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Resource Library
Equip library with books | Q1 Dec: 2022-12-16 | Librarian
Buy computer | Q2 Feb: 2023-02-12 | Secretary
Resource use training | Q2 Jan: 2023-01-15 | Librarian
Developing Diversity and Inclustion policy
Consultant undertaking research | Q2 Mar: 2023-03-12 | D&I consultant
Report due from consultant | Q2 Mar: 2023-03-25 | D&I consultant
Stakeholder meetings | Q1 Dec: 2022-12-15; Q2 Feb: 2023-02-20 | Secretary
Publication preparation for printing | Q2 Mar: 2023-03-02 | All team
Marketing of publication | Q2 Apr: 2023-04-02 | Marketing manager