## Sheet1
| Key |  | Activity on track
Activity delayed
Activity rescheduled
|  | 2022-03-04 | Deadline or date of activity
| Q1 |  |  | Q2 |  |  |  | Owner of activity | Notes
Activity | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Resource Library
Equip library with books |  |  | 2022-12-16 |  |  |  |  | Librarian
Buy computer |  |  |  |  | 2023-02-12 |  |  | Secretary
Resource use training |  |  |  | 2023-01-15 |  |  |  | Librarian
Developing Diversity and Inclustion policy
Consultant undertaking research | [5 empty] | 2023-03-12 |  | D&I consultant
Report due from consultant | [5 empty] | 2023-03-25 |  | D&I consultant
Stakeholder meetings |  |  | 2022-12-15 |  | 2023-02-20 |  |  | Secretary
Publication preparation for printing | [5 empty] | 2023-03-02 |  | All team
Marketing of publication | [6 empty] | 2023-04-02 | Marketing manager