## Sheet1
| Key |  | Activity on track
Activity delayed
Activity rescheduled
|  | 2023-06-04 | Deadline or date of activity
Y1
| Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Owner of activity | Notes
Activity | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
Resource Library
Equip library with books | [12 empty] | Librarian | bar: Q1 Oct to Q1 Nov; Q3 May to Q3 Jun
Buy computer | [12 empty] | Secretary | bar: Q1 Nov
Resource use training | Q2 Jan: 2023-01-15; Q4 Aug: 2023-08-11 | Librarian
Curriculum revision
Industry secondments | [12 empty] | Staff
Report due from secondments | Q2 Mar: 2023-03-25 | Staff
Stakeholder meetings | Q2 Feb: 2023-02-20; Q3 May: 2023-05-02; Q4 Aug: 2023-08-02 | Project lead
Preparation for approval | Q4 Sep: Print 15-Sep | All team